## Feature register
Aven UI and UX comparison
15 September 2026. Current Aven: ux-pipeline-v6. Reference differences are opportunities, not automatic requirements.
Observed = inspected UI, not end-to-end capability proof. Documented = official product docs. Unverified = not established.
Assessment: useful network-work foundation; incomplete interaction consistency, capability readiness and recovery.
Build order: 1 Basics → 2 Chat → 3 Trusted work → 4 Extend. Preserve existing strengths throughout.
Implementation pipeline active: fix Needs fix first, then Missing and Partial by dependency. Verified means tested; owner acceptance is separate.
Checks | 115 |  | Needs fix | 0 | Missing | 14 | Partial / placeholder | 29 | Present | 69 | Not verified | 3 | Verified | 71
ID | Area | Feature | Aven state | Aven today | Grok Bot | Codex desktop | Claude Code | Aven target / next action | Priority | Phase | Dependency | Acceptance check | Delivery | Decision | Evidence
UX-001 | Basics | Subtle scrollbars | Present | Thin scrollbars reveal on hover, focus or scrolling, then fade while idle. Wheel, keyboard, Chromium touch emulation, reduced-motion and forced-colors checked. | Observed: thin sidebar bar; fade timing untested [G1] | Observed: restrained scrollbars; fade timing untested [C0] | Unverified | Show subtle bars on hover or scroll, then fade. Keep scrolling usable. | P1 | 1 Basics | CSS overflow investigation | Mouse, keyboard and touch scrolling work. Idle bars fade. CLI whitespace stays exact. | Verified | Agreed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/{root-review.json,history-regression.json,reaction-recovery.json}; isolated browser checks exit 0. No provider/device calls; no physical-device or owner acceptance.
UX-002 | Basics | Contain horizontal overflow | Present | Long sidebar labels stay contained. Page bounds checked at 1440/1024/768/390; narrow windows collapse the rail. Raw CLI text remains unwrapped and exact. | Observed: single-line previews fit sidebar [G1] | Observed: previews fit sidebar [C0] | Unverified | Constrain row widths; only raw code and wide tables may scroll sideways. | P1 | 1 Basics | Long names and CLI fixtures | No horizontal sidebar or page scroll at agreed desktop widths. Long CLI lines remain copy-exact. | Verified | Agreed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/{root-review.json,history-regression.json,reaction-recovery.json}; isolated browser checks exit 0. No provider/device calls; no physical-device or owner acceptance.
UX-003 | Basics | Account entry | Present | Account caret removed; keyboard account menu and Settings remain accessible. | Observed: account row without that caret [G1] | Observed: account control at bottom [C0] | Unverified | Remove caret while keeping account and Settings access discoverable. | P2 | 1 Basics | None | Caret absent; account menu remains keyboard reachable. | Verified | Agreed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/root-identity-review.json; review-ux-pipeline.cjs --identity-only; exit 0. Isolated Chromium, owner acceptance pending.
UX-004 | Basics | Selected profile identity | Present | Profile heading shows selected coworker name; redundant selector removed. Rename synchronizes profile and conversation. | Observed: selected bot settings; name field [G1] | Unverified | Unverified | Use actual coworker name as heading. Remove redundant Agent switcher. | P1 | 1 Basics | Selected chat identity | Firewall opens firewall profile. Rename synchronizes header. Editing and documents remain accessible. | Verified | Agreed | 2026-09-15: root-identity-review.json and root-profile-desktop.png under .intentgraph/evidence/ux-fixes-2026-09-15/; browser test exit 0. Owner acceptance pending.
UX-005 | Basics | Horizontal reaction panel | Present | Six emoji and More form one horizontal row above text actions. Keyboard navigation, viewport bounds and focus return verified. Reply is tracked separately in UX-024. | Observed: six emoji plus More, above Reply and Copy [G1] | Unverified | Unverified | Reproduce observed compact horizontal row and separate text actions. | P1 | 1 Basics | G1 message-menu capture | Row matches reference structure; opens by mouse and keyboard without clipping. | Verified | Agreed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/{root-review.json,history-regression.json,reaction-recovery.json}; isolated browser checks exit 0. No provider/device calls; no physical-device or owner acceptance.
UX-006 | Basics | One reaction per user | Present | One local reaction: selecting another replaces it, selecting the same clears it. Latest legacy reaction retained with raw backup and save-failure recovery. | Unverified | Unverified | Unverified | New reaction replaces prior selection; same reaction toggles off. | P1 | 1 Basics | Existing reaction migration | Select A then B leaves only B. Selecting B clears it. Reload preserves result without losing messages. | Verified | Agreed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/{root-review.json,history-regression.json,reaction-recovery.json}; isolated browser checks exit 0. No provider/device calls; no physical-device or owner acceptance.
UX-007 | Navigation | Coworker-first entry | Present | Coworker-first creation and navigation. Existing grouped histories remain reachable under Conversations; archive/revert/drafts/queue regressions pass. | Observed: direct bot list; New Bot and New Channel [G1] | Observed: task and project organization [C0] | Documented: session and folder organization [D1] | Choose named coworker and chat. Remove Teams from primary experience. | P1 | 1 Basics | Preserve and expose all existing grouped histories | New user can start a named conversation without understanding teams. Existing chats, drafts, queues and avatars remain accessible. | Verified | Agreed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/{root-review.json,history-regression.json,reaction-recovery.json}; isolated browser checks exit 0. No provider/device calls; no physical-device or owner acceptance.
UX-008 | Navigation | Stable conversation header | Present | Selected coworker name remains in center header. | Observed: persistent bot name [G1] | Observed: persistent task title [C0] | Documented: session title [D1] | Keep stable identity during sending, streaming and pane changes. | P2 | Keep | Regression verification | Short first message never replaces coworker identity. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/ux-fixes-2026-09-15/history-regression.json (stable coworker title after hi); .intentgraph/runtime/verify-direct-teams.cjs:8,12 Owner acceptance remains separate.
UX-009 | Navigation | Sidebar previews | Present | Readable plain-text sidebar previews; full stored Markdown and message text are unchanged. | Observed: name, preview, time and unread dot [G1] | Observed: titles and activity indicators [C0] | Documented: session sidebar [D1] | Use plain-text previews with time and useful state. | P2 | 2 Chat | Message text normalization | Markdown table syntax and code fences do not overwhelm the row. Full title remains accessible. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/local-commands.json; browser test exit 0. Mocked requests; owner acceptance pending.
UX-010 | Navigation | Pin important conversations | Present | Pin controls exposed for conversations. | Unverified | Documented: pin chats and projects [C2] | Documented: session organization [D1] | Keep pin behavior and make state obvious. | P2 | Keep | Persistence regression | Pinned items remain accessible and retain order after reload. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/project-navigation.json (pin/reload/order) Owner acceptance remains separate.
UX-011 | Navigation | Rename conversations | Present | Chat actions and naming flows exist. | Unverified | Documented: rename chats [C2] | Documented: session management [D1] | Keep rename distinct from coworker rename. | P2 | Keep | Identity rules | Renaming a conversation never renames its coworker unexpectedly. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/pending-88-20260916/preserved-audit.json (chatTitle changed; coworkerName unchanged) Owner acceptance remains separate.
UX-012 | Navigation | Sections and ordering | Present | Sections can be renamed and moved up/down. Boundaries are disabled, order persists after reload, and failed saves preserve order and focus. Grouping retains existing conversation histories. | Observed: Direct and custom sections [G1] | Observed: Pinned and Projects [C0] | Documented: sessions grouped in sidebar [D1] | Use optional lightweight folders after coworker-first entry is clear. | P2 | 2 Chat | UX-007 | Grouping never implies coordinated agent execution or hides old histories. | Verified | Proposed | 2026-09-16: navigation.json; isolated browser test exit 0. Section boundaries, reload, failed-save atomicity and focus verified. Owner acceptance pending.
UX-013 | Navigation | Sidebar collapse and resize | Present | Collapse and resize controls implemented. | Unverified | Observed: collapsible sidebar and split pane [C0] | Documented: adjustable pane layout [D1] | Preserve width and keyboard resizing. | P2 | Keep | Responsive checks | Collapse and resize leave active chat and composer usable. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/pending-88-20260916/accessibility-results.json (UX096 PASS at 320/390/760/1440; page/body bounds); .intentgraph/evidence/project-navigation.json (persistent collapse) Owner acceptance remains separate.
UX-014 | Navigation | Back and forward navigation | Present | Internal conversation Back/Forward preserves each draft and scroll position. Valid session history survives reload; new visits truncate forward history. Unsaved document guards remain active. | Unverified | Observed: back and forward controls [C0] | Unverified | Add predictable history navigation if user workflows require it. | P3 | 2 Chat | Navigation state review | Back returns to previous chat without dropping draft or executing a request. | Verified | Investigate | 2026-09-16: navigation.json; isolated browser test exit 0. Draft/scroll, reload, forward history, invalid storage, unsaved guards and 320-1440px bounds verified. No provider calls. Owner acceptance pending.
UX-015 | Search | Workspace search | Present | Dialog searches names, saved messages and attachment names. | Observed: search field [G1] | Documented: search chats [C2] | Documented: session search [D1] | Keep local search with clear scope and keyboard entry. | P2 | Keep | Result accuracy checks | Known saved phrase resolves to the correct conversation. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/ux-fixes-2026-09-15/history-navigation.json (saved phrase, coworker/conversation filters, exact result navigation) Owner acceptance remains separate.
UX-016 | Search | Search filters and results | Present | Coworker, conversation and result-type filters; snippets, destinations, empty state and exact message focus verified. | Unverified | Documented: project and chat search [C2] | Unverified | Show result type, snippet and destination; make empty results useful. | P2 | 2 Chat | Search index | Filter by coworker or conversation and open exact result context. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/history-navigation.json; verify-history-navigation.cjs exit 0. Isolated mocked chat; owner acceptance pending.
UX-017 | Search | Find within conversation | Present | In-conversation find with Ctrl/Cmd+F, occurrence count, previous/next, exact text highlights and focus restoration. | Unverified | Documented: find in chat [C4] | Documented: transcript search [D2] | Add match count, previous/next, and scroll-to-message. | P2 | 2 Chat | Message IDs | Searching a repeated term visits every match without losing composer draft. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/chat-interactions.json; verify-chat-interactions.cjs exit 0. Mocked requests; owner acceptance pending.
UX-018 | Search | Command palette | Present | Searchable command palette with keyboard navigation, context availability, modal safety and focus restoration. | Unverified | Documented: command menu [C4] | Documented: slash command list [D2] | Add searchable actions with shortcuts, disabled reasons and context. | P2 | 2 Chat | Stable action registry | Keyboard opens palette; selected action works in current chat; Escape restores focus. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/local-commands.json; browser test exit 0. Mocked requests; owner acceptance pending.
UX-019 | Composer | Multiline input and send | Present | Textarea, attachment button and disabled-empty send. | Observed: compact message field [G1] | Observed: composer with send/stop [C0] | Documented: prompt input [D1] | Keep familiar Enter and Shift+Enter behavior and a compact idle composer. | P2 | Keep | IME and long-input checks | Empty send disabled. Multiline text and IME composition do not send accidentally. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/pending-88-20260916/preserved-audit.json (emptyDisabled=true, multilineHeld=true, imeHeld=true, calls=0) Owner acceptance remains separate.
UX-020 | Composer | Draft preservation | Present | Per-chat drafts are stored locally. | Unverified | Unverified | Documented: session context [D1] | Preserve drafts across chat switches and reload. | P1 | Keep | Storage regression | Two chats retain different unsent drafts after switching and reload. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/ux-pipeline-2026-09-16/navigation.json (back/forward preserves two drafts and reload) Owner acceptance remains separate.
UX-021 | Composer | Attachment selection and removal | Present | Selected UTF-8 text files are validated locally. Explicit Send includes exact contents in saved request text. Unsupported files remain labeled/removable; previous-session names require reattachment. | Observed: attachment entry visible [G1] | Documented: files and folders [C1] | Documented: file and image attachment [D1] | Show file type, size, readiness, removal and errors before send. | P1 | 2 Chat | Backend attachment support | Unsupported attachments are labeled before send; supported contents reach model context. | Verified | Proposed | 2026-09-16: attachments.json; verify-attachments-unit.cjs. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-022 | Composer | Drag-drop and clipboard files | Present | Composer file drop and clipboard-file paste create usable text attachments; unsupported and oversized files give recovery instructions. | Unverified | Unverified | Documented: drag-drop attachments [D1] | Implement only supported types with visible readiness. | P2 | 2 Chat | UX-020 | Paste/drop valid file creates one usable attachment. Invalid type shows recovery. | Verified | Investigate | 2026-09-16: attachments.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-023 | Composer | File or device mentions | Missing | No contextual @ picker in active shell. | Unverified | Documented: file search and context [C4] | Documented: @ file mentions [D1] | Add @device and @document chips that identify exact scope. | P2 | 3 Trusted work | Inventory/document context contract | Mention resolves to a stable ID; unavailable devices cannot appear connected. | Not started | Proposed | polished.html; polished.js; polished.js:213-265,408-437
UX-024 | Composer | Reply to a message | Present | Reply selects a cancellable, saved quote. Explicit Send or queue carries the bounded quote; reload, limits and absent target handling verified. | Observed: Reply menu action [G1] | Unverified | Documented: side questions, not equivalent [D1] | Add reply preview with cancel and a link to original message. | P2 | 2 Chat | Message IDs and context rules | Reply identifies source message; cancel removes reference without deleting draft. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/chat-interactions.json; verify-chat-interactions.cjs exit 0. Mocked requests; owner acceptance pending.
UX-025 | Composer | Edit and resend a prompt | Present | Explicit edit and resend; original history recoverable in a local copy, composer draft preserved, busy/queue and length guards verified. | Unverified | Unverified | Documented: prompt history and rewind [D2] | Support editing with explicit context boundary and retained history. | P2 | 2 Chat | Revert safeguards | User can review edited prompt before send; earlier device commands are never reversed or repeated silently. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/edit-rendering.json; browser test exit 0. Mocked requests; owner acceptance pending.
UX-026 | Composer | Voice dictation | Missing | No microphone input in Aven. | Observed: microphone button visible; transcription untested [G1] | Observed: microphone button visible [C0] | Documented: voice input [D2] | Defer until microphone, transcript review and provider privacy are defined. | P3 | 4 Extend | Voice backend and permission UX | Recording indicator and cancel work; transcript is editable before sending. | Not started | Proposed | polished.html composer; polished.js:213-265,408-437
UX-027 | Composer | Model and effort picker | Partial | Active OpenCode shown; preferred model field does not change runtime. | Unverified | Observed: model and effort in composer [C0] | Documented: model and effort controls [D1] | Show actual model; enable selection only for connected supported providers. | P1 | 3 Trusted work | Provider routing | Picker change is reflected in the next request and response provenance. | Not started | Proposed | A0 Settings Models; agent-runtime.cjs; polished.js:213-265,408-437
UX-028 | Execution | Streamed response and activity | Present | Chat streams and expandable activity/evidence exist. | Observed: message transcript [G1] | Observed: progress summaries [C0] | Documented: live transcript [D1] | Preserve smooth updates and readable final result. | P1 | Keep | Stream regression | No duplicate final text or evidence when a stream finishes. | Verified | Preserve | 2026-09-16: preservation audit PASS. isolated run `node .intentgraph/runtime/verify-agent-stream-ui.cjs`; .intentgraph/evidence/chat-polish.json (one terminal despite duplicate event/final) Owner acceptance remains separate.
UX-029 | Execution | Stop a running request | Present | Stop aborts the request, pauses queued work and explicitly marks submitted remote completion UNKNOWN. Captured evidence remains inspectable. | Unverified | Observed: stop button during active task [C0] | Documented: interrupt control [D1] | Distinguish stopping the model, current tool and queued work. | P1 | 3 Trusted work | Abort propagation | Stop state is truthful; cancellation does not claim a completed device command was undone. | Verified | Proposed | 2026-09-16: verify-queue-terminal.cjs 4/4; run-durability.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-030 | Execution | Queue follow-up messages | Present | Visible queue with per-item controls exists. | Unverified | Unverified | Documented: redirect while working [D1] | Keep queue separate from immediate steering. | P1 | Keep | Queue regression | Queued messages stay ordered and are never submitted twice. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/pending-88-20260916/preserved-audit.json (storage failure: 0 calls, queue retained; recovery: 1 call); .intentgraph/runtime/verify-queue-terminal.cjs:49-75 Owner acceptance remains separate.
UX-031 | Execution | Queue edit, remove and resume | Present | Saved queue and resume control exist. | Unverified | Unverified | Unverified | Keep explicit recovery after interrupted processing. | P1 | Keep | Queue persistence | Reload retains queue; resume is intentional; editing changes only selected item. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/runtime/verify-queue-terminal.cjs:49-75,120-128 (FIFO/edit/remove/resume/reload pause) Owner acceptance remains separate.
UX-032 | Execution | Steer the next step | Present | Separate Steer next step button. | Unverified | Unverified | Documented: correction after current action [D1] | Keep acknowledgment and timing visible. | P1 | Keep | Runtime steer support | Correction applies before next tool step and does not silently create a duplicate run. | Verified | Preserve | 2026-09-16: preservation audit PASS. 25/25 local fixture tests passed, including `intentgraph/steering.test.cjs:166-191` (next model boundary, applied once); .intentgraph/runtime/verify-queue-terminal.cjs:77-118 Owner acceptance remains separate.
UX-033 | Execution | Clarification and approval cards | Partial | No general rich choice/reply card comparable to reference observed. | Observed: inline question with choices and dismissed state [G1] | Unverified | Documented: permission prompts [D1] | Use compact choices, free-text answer and explicit waiting state. | P1 | 3 Trusted work | Structured pending-input events | Answer maps to one pending question; stale cards cannot authorize later work. | Not started | Proposed | A0; server/runtime source review; polished.js:193-255,380-422; intentgraph/server.cjs:206-285
UX-034 | Execution | Plan and inspect modes | Present | Plan uses zero tools at the backend. Inspect retains the allowlisted read-only runtime. Mode persists and queued requests retain their original mode. | Unverified | Documented: plan mode entry [C1] | Documented: Plan permission mode [D1] | Separate discussion/inspection from any future device changes. | P1 | 3 Trusted work | Runtime-enforced mode contract | Plan mode cannot execute state-changing operations; current read-only scope stays explicit. | Verified | Proposed | 2026-09-16: verify-chat-modes.cjs and modes-ui.json passed; malicious tool-call fixture invokes no sandbox. No live provider call.
UX-035 | Execution | Detailed tool transcript | Present | Expandable activity and raw CLI details. | Unverified | Observed: collapsible tool activity [C0] | Documented: normal, verbose and summary views [D1] | Make summary concise and details inspectable. | P2 | Keep | Evidence provenance | Summary, tool input and actual result remain distinguishable. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/runtime/verify-queue-terminal.cjs:77-118 (tool input/result/status/raw output distinct); isolated stream UI passed Owner acceptance remains separate.
UX-036 | Execution | Run state and elapsed time | Present | Run metadata retains elapsed time and SUCCESS/FAILURE/UNKNOWN outcome. Interrupted runs show a visible uncertainty notice rather than completed success. | Observed: time and unread state [G1] | Observed: running indicators [C0] | Documented: session activity [D1] | Use consistent queued/running/waiting/stopped/failed/completed states. | P1 | 3 Trusted work | Unified run state | A failed or interrupted run cannot display completed success; elapsed time stops correctly. | Verified | Proposed | 2026-09-16: run-recovery.json; run-durability.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-037 | Execution | Parallel work visibility | Missing | Backend uses one global in-flight request; team members are not parallel work. | Unverified | Observed: multiple tasks and child-agent progress [C0] | Documented: parallel isolated sessions [D1] | Show current serial limit honestly; add independent work only with backend support. | P2 | 4 Extend | Scheduler, isolation and per-run IDs | Two runs remain isolated, individually stoppable and recoverable. | Not started | Proposed | server.cjs chatPending; architecture.json; polished.js:193-255,380-422; intentgraph/server.cjs:206-285
UX-038 | Execution | Context and usage visibility | Present | Run details show actual response model and supported token metadata. Missing usage is Unavailable. Existing context preview reports the bounded message window. | Unverified | Unverified | Documented: context and plan usage [D1] | Expose real per-run usage and limits when provider supplies them. | P2 | 3 Trusted work | Usage event contract | Unknown usage displays unavailable; displayed model and token totals match actual response data. | Verified | Proposed | 2026-09-16: run-recovery.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-039 | Execution | Retry with retained evidence | Partial | Failures are surfaced; contextual retry needs an explicit contract. | Unverified | Unverified | Unverified | Offer safe retry with original prompt, visible scope and duplicate-action protection. | P1 | 3 Trusted work | Run IDs and evidence history | Retry does not repeat completed device actions silently; partial evidence remains inspectable. | Not started | Proposed | polished.js request errors; server.cjs; polished.js:193-255,380-422; intentgraph/server.cjs:206-285
UX-040 | Execution | Resume after app restart | Present | Bounded local run journals persist stream evidence. Restart recovers one incomplete record and pauses queued work without re-execution; save failures retain recovery state. | Unverified | Documented: long-running work [C5] | Documented: resume sessions [D2] | Recover pending work with truthful stopped/recoverable status. | P1 | 3 Trusted work | Durable run checkpoints | Restart during work preserves transcript and exposes recovery without duplicate execution. | Verified | Proposed | 2026-09-16: run-recovery.json; run-durability.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-041 | Messages | Readable Markdown | Present | Common Markdown headings, lists, tables, emphasis, inline and fenced code render safely with preserved source text. | Observed: formatted paragraphs and fixed-width text [G1] | Observed: formatted text and lists [C0] | Documented: formatted transcript [D1] | Harden lists, tables, code, links and long content. | P2 | 2 Chat | Renderer fixtures | Representative network reports remain readable; untrusted HTML cannot execute. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/edit-rendering.json; browser test exit 0. Mocked requests; owner acceptance pending.
UX-042 | Messages | Code blocks and exact copy | Present | Raw CLI appears once with exact-copy controls. | Observed: fixed-width report observed [G1] | Unverified | Documented: terminal and transcript [D1] | Preserve byte-faithful CLI evidence and separate formatted interpretation. | P1 | Keep | CLI regression | Spaces, tabs and line breaks survive copy; no duplicate raw output. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/runtime/verify-queue-terminal.cjs:77-118 (exact raw whitespace/copy); .intentgraph/evidence/ux-fixes-2026-09-15/root-review.json Owner acceptance remains separate.
UX-043 | Messages | Copy messages | Present | Copy question/answer and menu action exposed. | Observed: Copy action [G1] | Unverified | Unverified | Preserve accessible feedback and reliable text extraction. | P2 | Keep | Clipboard regression | Copy uses correct message and reports failure without claiming success. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/pending-88-20260916/preserved-audit.json (clipboard denial reports failure); .intentgraph/evidence/message-tools.json (answer/question copy) Owner acceptance remains separate.
UX-044 | Messages | Time grouping and metadata | Present | Local date separators and focusable timestamps with full accessible date/time. Invalid timestamps do not invent dates. | Observed: date separators and exact time [G1] | Unverified | Unverified | Keep secondary time metadata and group dates without clutter. | P3 | 2 Chat | Date/time formatting | Old and new days are clear; full timestamp accessible on focus or hover. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/history-navigation.json; verify-history-navigation.cjs exit 0. Isolated mocked chat; owner acceptance pending.
UX-045 | Messages | Follow latest without jumping | Present | Output preserves older reading position; explicit keyboard Jump to latest and near-bottom following use a 120px threshold. | Unverified | Unverified | Unverified | Autofollow only near bottom; offer jump-to-latest when reading older work. | P1 | 2 Chat | Scroll state test | New output does not pull user away from an older message; latest button is keyboard usable. | Verified | Investigate | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/history-navigation.json; verify-history-navigation.cjs exit 0. Isolated mocked chat; owner acceptance pending.
UX-046 | Messages | Conversation revert and undo | Present | Context-only revert stores removed history and undo. | Unverified | Unverified | Documented: rewind/checkpoints [D2] | Preserve explicit boundary: chat context changes do not undo device commands. | P1 | Keep | History mutation regression | Revert and undo restore exact message history; busy or queued state is protected. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/ux-fixes-2026-09-15/history-regression.json (revert no execution, undo after reload); .intentgraph/runtime/verify-edit-rendering.cjs:1-16 (queued edit disabled) Owner acceptance remains separate.
UX-047 | Messages | Fork or side conversation | Present | Named local forks retain the selected message prefix and raw provenance. Parent history/draft/queue unchanged; origin link survives reload and storage failures roll back. | Unverified | Documented: side chat [C4] | Documented: side chat [D1] | Add context-preserving exploration without replacing the main investigation. | P2 | 3 Trusted work | Durable conversation IDs | Branch retains provenance and can be revisited without mutating parent history. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/history-navigation.json; verify-history-navigation.cjs exit 0. Isolated mocked chat; owner acceptance pending.
UX-048 | Messages | Direct links to evidence/messages | Present | Copy a local message link and open its exact saved chat/message. Missing and archived destinations give explanations. Links are scoped to this browser workspace. | Unverified | Documented: chat deep links [C4] | Unverified | Add stable links for local navigation and exported evidence. | P2 | 3 Trusted work | Persistence and permissions | Link opens correct conversation/message; missing or archived targets have a clear explanation. | Verified | Proposed | 2026-09-16: run-recovery.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-049 | Messages | Reaction picker beyond defaults | Present | More opens ten additional reactions. Selection, replacement, clearing and reload use the same single local reaction rule. | Observed: More emoji control [G1] | Unverified | Unverified | Add a compact accessible picker only after single-reaction behavior is correct. | P3 | 2 Chat | UX-005 and UX-006 | Picker supports search/navigation and closes without moving the message. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/{root-review.json,history-regression.json,reaction-recovery.json}; isolated browser checks exit 0. No provider/device calls; no physical-device or owner acceptance.
UX-050 | History | Archive and restore | Present | Settings contains Archived chats; empty state observed. | Unverified | Documented: archive and restore in Settings [C2] | Documented: archive sessions [D1] | Keep recoverable archive separate from deletion. | P1 | Keep | Archive regression | Archived chat is read-only until restored; messages and evidence survive. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/project-navigation.json (archive/restore/reload and busy guard); .intentgraph/evidence/ux-fixes-2026-09-15/history-navigation.json (archived read-only) Owner acceptance remains separate.
UX-051 | History | Export conversations and evidence | Present | Workspace JSON and selected conversation Markdown exports include timestamps, drafts, notes and exact raw evidence. Backend credentials and attachment contents are not read. | Unverified | Unverified | Documented: transcript export [D2] | Provide human-readable report plus structured evidence export. | P2 | 3 Trusted work | Redaction and provenance | Export contains correct selected scope, timestamps and exact evidence without credentials. | Verified | Proposed | 2026-09-15: local-data-ui.json; browser test exit 0. verify-backup-schema.cjs 9/9 passed, including private-field rejection, exact evidence, UTF-8 size boundary and interrupted-import recovery. Owner acceptance pending.
UX-052 | History | Import and backup recovery | Present | Validated import preview. Add mode remaps collisions and preserves existing work; explicit Replace keeps a recovery backup. Imported queues pause. Write failures and interrupted imports recover before startup migration. | Unverified | Unverified | Unverified | Add validated restore preview with conflict handling. | P1 | 3 Trusted work | Versioned storage schema | Invalid backup changes nothing. Valid restore preserves unrelated current work. | Verified | Proposed | 2026-09-15: local-data-ui.json; browser test exit 0. verify-backup-schema.cjs 9/9 passed, including private-field rejection, exact evidence, UTF-8 size boundary and interrupted-import recovery. Owner acceptance pending.
UX-053 | History | Durable cross-device histories | Missing | Browser storage is local; no account sync or tenant history service. | Unverified | Unverified | Documented: local/cloud sessions, different scope [D1] | Defer sync until identity and ownership contracts exist. | P2 | 4 Extend | 2026-09-16 user decision: keep cross-device history, accounts/customer isolation and remote handoff pending; finish local features first. | Two devices show consistent authorized history with explicit conflict handling. | Deferred | Proposed | architecture.json; polished.js persistence; polished.js:19-58,158-174,460,481
UX-054 | Coworkers | Avatar family and appearance | Present | Expanded avatar family and appearance chooser. | Observed: distinct bot avatars [G1] | Unverified | Unverified | Keep approved artwork and persistent selection. | P2 | Keep | Avatar regression | Saved avatars remain the same after migration and reload. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/avatar-family-app-qa-results.json (all avatar choices/custom color/photo/migration/reload; no external requests); .intentgraph/runtime/verify-backup-schema.cjs:4,15-28 Owner acceptance remains separate.
UX-055 | Coworkers | Name, label and description | Present | Editable profile fields exist. | Observed: name, label and description [G1] | Unverified | Unverified | Keep plain editing and save feedback. | P2 | Keep | UX-004 | Long name remains readable; saved changes update selected coworker only. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/ux-fixes-2026-09-15/root-identity-review.json (profile identity/rename sync); .intentgraph/avatar-family-app-qa-results.json (long-name responsive fixture) Owner acceptance remains separate.
UX-056 | Coworkers | Behavior and document access | Partial | Local SOUL.md/MEMORY.md editor exists. Chat request sends agent name and messages, not these documents. | Unverified | Documented: agent instructions and skills [C6] | Documented: shared configuration [D1] | Make behavior instructions and memory distinguishable and inspectable. | P1 | 3 Trusted work | Explicit behavior/memory runtime injection | Editing document explains effect and scope; saved content is the content actually used. | Not started | Proposed | polished.js:272-280,314,408-422; agent-runtime.cjs:363
UX-057 | Coworkers | Notification preference | Partial | Muted coworkers suppress local completion notices. Enabled notices open the finished message. Waiting/error attention alerts remain pending. | Observed: completion/input notification switch [G1] | Documented: notifications [C1] | Unverified | Connect preference to real delivery or mark it unavailable. | P1 | 3 Trusted work | Notification event channel | Muted coworker stays quiet; enabled alerts link to the correct finished/waiting run. | Implemented | Proposed | 2026-09-16: alerts.json. Implemented slice verified; full feature remains pending.
UX-058 | Coworkers | Simple creation and first welcome | Partial | Creation plus local welcome exist; mental model remains confusing. | Observed: New Bot entry [G1] | Observed: New chat [C0] | Documented: New session [D1] | Use name, purpose and appearance with a clear first action. | P1 | 2 Chat | UX-007 | Welcome is visibly local and never sent as fabricated model history. | Not started | Proposed | polished.js coworker creation; polished.js:272-314,472-479
UX-059 | Settings | Appearance and density | Present | Comfortable and Compact density styles with light/dark themes. Save, cancel, reload and storage-failure behavior verified. | Unverified | Unverified | Documented: theme/display options [D2] | Keep restrained theme and readable density options. | P2 | Keep | Theme and contrast verification | Both themes preserve readable controls and evidence; settings persist. | Verified | Preserve | 2026-09-15: local-data-ui.json; browser test exit 0. verify-backup-schema.cjs 9/9 passed, including private-field rejection, exact evidence, UTF-8 size boundary and interrupted-import recovery. Owner acceptance pending.
UX-060 | Settings | Live provider setup | Partial | Removed cosmetic provider-switch controls. Settings shows actual fixed runtime and user-triggered configuration snapshot. Provider switching/setup remains pending. | Unverified | Observed: current model label [C0] | Documented: model selector [D1] | Add explicit connected/tested/unavailable states for each supported provider. | P1 | 3 Trusted work | Provider adapters and secure credential flow | Changing provider cannot silently leave a different runtime active. No secrets in UI output. | Implemented | Proposed | 2026-09-16: diagnostics-ui.json. Implemented slice verified; full feature remains pending.
UX-061 | Settings | Connections health | Partial | Local configuration/status snapshots refresh with an explicit check time. Reachability and live provider/device health remain unverified. | Observed: Plugins navigation [G1] | Observed: Plugins navigation [C0] | Documented: connectors/plugins [D1] | Show actual connection, last checked time, supported actions and recovery. | P1 | 3 Trusted work | Adapter health checks | Disconnected adapter cannot look ready; refresh updates from real state. | Implemented | Proposed | 2026-09-16: diagnostics-ui.json. Implemented slice verified; full feature remains pending.
UX-062 | Settings | Privacy and data controls | Partial | Local privacy/data preferences exist; service-level controls absent. | Unverified | Unverified | Unverified | Explain local versus transmitted data and make export/reset scope explicit. | P1 | 3 Trusted work | Storage and provider contracts | User can identify what stays local and what a request sends; destructive actions are recoverable where promised. | Not started | Proposed | polished.js privacy settings; architecture.json; polished.js:480-482
UX-063 | Settings | Real account and sign-out | Placeholder | Account menu exists but Settings states no account connected. | Observed: account row [G1] | Observed: account row [C0] | Unverified | Hide unsupported account switching or clearly identify local profile. | P1 | 2 Chat | 2026-09-16 user decision: keep cross-device history, accounts/customer isolation and remote handoff pending; finish local features first. | No control suggests remote sign-in or sign-out succeeded when it only changes local display. | Deferred | Proposed | A0; polished.html account-menu; polished.js:480-482
UX-064 | Settings | Help and feedback | Present | Help opens keyboard/local workspace guidance. Feedback saves locally and can be downloaded manually; no private logs or network submission are attached. | Unverified | Unverified | Unverified | Provide accurate supported features, shortcuts and local diagnostics export. | P2 | 2 Chat | Support destination decision | Every help entry opens useful information; feedback never silently sends private logs. | Verified | Proposed | 2026-09-16: diagnostics-ui.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-065 | Settings | Shortcut reference | Present | Shortcut reference generated from the active command registry; Ctrl/Cmd+K and Ctrl/Cmd+F verified. | Unverified | Documented: shortcut reference and customization [C4] | Documented: Ctrl+/ shortcut list [D1] | Add short searchable shortcut reference; avoid conflicting bindings. | P2 | 2 Chat | Action registry | Displayed shortcuts work and unavailable actions are not advertised. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/local-commands.json; browser test exit 0. Mocked requests; owner acceptance pending.
UX-066 | Outputs | Artifact library for real chats | Partial | Artifacts now list actual saved raw evidence outputs for the selected chat, with exact downloads and provenance. General generated-file registry remains pending. | Unverified | Documented: work with files and artifacts [C1] | Documented: HTML/PDF previews [D1] | Connect saved output files to the run that created them. | P1 | 3 Trusted work | Artifact storage and provenance | Real chat artifact opens correct file; another chat never inherits sample output. | Implemented | Proposed | 2026-09-16: workspace-shell.json. Implemented slice verified; full feature remains pending.
UX-067 | Outputs | Browser preview | Placeholder | Aven preview is static. Separate IntentGraph browser adapter has approval/digest controls. | Unverified | Observed: working embedded browser [C0] | Documented: Browser pane [D1] | Use a real bounded preview with URL, loading, errors and navigation controls. | P2 | 4 Extend | Connect existing browser adapter to Aven UI | Preview shows actual current content and truthful unavailable states. | Not started | Proposed | polished.js:359-370; intentgraph/adapters/index.cjs:329-503
UX-068 | Outputs | Computer preview and control | Placeholder | Aven preview is static. Separate IntentGraph desktop adapter targets selected windows. | Observed: bot screen entry; execution untested [G1] | Documented: computer use [C1] | Documented: computer use [D1] | Do not imply a live desktop until session and permissions are real. | P3 | 4 Extend | Integrate existing desktop adapter and approval UX | Stale or unavailable screen is labeled; controls apply only to authorized session. | Not started | Proposed | polished.js:359-370; intentgraph/adapters/index.cjs:524-598
UX-069 | Outputs | Resizable work panes | Partial | Right pane exists; general multi-pane layout is limited. | Observed: profile/screen pane [G1] | Observed: side-by-side chat and browser [C0] | Documented: drag-drop panes [D1] | Support focused chat plus one useful evidence/output pane first. | P2 | 3 Trusted work | Responsive pane model | Opening evidence preserves enough room to read and type; close returns focus. | Not started | Proposed | A0; polished.css right-pane; polished.js:319-370
UX-070 | Outputs | File tree and editor | Missing | No full file browsing/editor workspace. | Unverified | Documented: file tree and search [C4] | Documented: integrated file editor [D1] | Defer IDE parity; prioritize network documents and config review. | P3 | 4 Extend | Filesystem adapter and product scope | Only authorized files are shown and edits have explicit save/diff behavior. | Not started | Proposed | polished.html; polished.js; polished.js:319-370
UX-071 | Outputs | Interactive terminal | Missing | Raw diagnostic output exists, not a general interactive shell. | Unverified | Documented: integrated terminal [C6] | Documented: terminal pane [D1] | Keep read-only evidence primary; add terminal only for defined authorized workflows. | P3 | 4 Extend | Execution boundaries | User sees target/session and permissions; raw evidence remains separately retained. | Not started | Proposed | architecture.json; polished.js; polished.js:319-370
UX-072 | Review | Before/after change review | Missing | No general structured config diff approval workflow. | Unverified | Documented: diff review and scope selection [C3] | Documented: visual diffs [D1] | Adapt review to network configuration: exact target, diff, impact and approval. | P1 | 3 Trusted work | Change proposal/approval backend | Proposal shows exact diff and target; edits invalidate prior approval. | Not started | Proposed | polished.html; architecture.json; intentgraph/adapters/index.cjs:462-503,570-598; polished.js:359-370
UX-073 | Review | Inline evidence annotations | Missing | No line-specific review comments found. | Unverified | Documented: inline comments [C3] | Documented: inline diff comments [D1] | Attach comments to immutable evidence line and run IDs. | P2 | 3 Trusted work | Evidence identity | Comment cannot drift to a different result after rerun. | Not started | Proposed | polished.js evidence UI; intentgraph/adapters/index.cjs:462-503,570-598; polished.js:359-370
UX-074 | Review | Execution approval receipt | Partial | Separate adapters implement one-time digest-bound approval. Aven lacks integrated general approval UI. | Unverified | Documented: agent approvals [C6] | Documented: permission modes [D1] | Preserve read-only safety; require exact scope-bound approval for future changes. | P1 | 3 Trusted work | Integrate existing receipt flow; define future network write scope | Target or command changes require new review; old approval cannot authorize new work. | Not started | Proposed | intentgraph/adapters/index.cjs:462-503,570-598; polished.js:359-370
UX-075 | Review | Git stage, commit and PR controls | Missing | No Git workflow in Aven. | Unverified | Documented: stage, revert, commit, PR review [C3] | Documented: PR monitoring [D1] | Defer; only add if configuration-as-code becomes a primary workflow. | P3 | 4 Extend | Repository integration and product scope | Git operations have clear repository and diff scope; no hidden publish. | Not started | Proposed | polished.html; polished.js; intentgraph/adapters/index.cjs:462-503,570-598; polished.js:359-370
UX-076 | Network | Device inventory selection | Partial | Backend inventory/diagnostics exist; composer lacks clear scope selection. | Unverified | Unverified | Unverified | Make selected devices and connection state visible before diagnostic work. | P1 | 3 Trusted work | Inventory adapter | User can see exact selected devices; aliases resolve consistently to evidence IDs. | Not started | Proposed | polished.js:332-357; intentgraph/agent-runtime.cjs:271-338
UX-077 | Network | Read-only scope visibility | Partial | Coworker welcome states read-only; scope is not consistently visible. | Unverified | Documented: permission modes [C6] | Documented: permission mode selector [D1] | Show concise current access scope near relevant actions. | P1 | 3 Trusted work | Runtime-enforced capability state | Read-only label agrees with enforced tool set; no confusing change/run action is offered. | Not started | Proposed | A0; agent-runtime.cjs; intentgraph/agent-runtime.cjs:203-214,271-415
UX-078 | Network | Evidence provenance and timestamps | Present | Raw diagnostics and investigation evidence are retained. | Unverified | Unverified | Unverified | Keep device, command, time and actual result together. | P1 | Keep | Evidence schema regression | Copied/exported evidence traces to exact run and command; generated narrative is distinguishable. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/pending-88-20260916/preserved-audit.json (Markdown has run-42 and command/target); .intentgraph/evidence/ux-fixes-2026-09-15/local-data-ui.json (raw export) Owner acceptance remains separate.
UX-079 | Network | Success versus healthy status | Partial | Current work explicitly avoids equating command success with network health. | Unverified | Unverified | Unverified | Use separate execution outcome and interpreted health assessment. | P1 | Keep | Status semantics regression | Successful command on faulty device cannot appear as healthy solely from exit status. | Verified | Preserve | 2026-09-16: preservation audit PASS. preserved-audit.json: top-level SUCCESS with nested FAILURE renders FAILURE; run state outcome precedence verified Owner acceptance remains separate.
UX-080 | Network | Scope, impact and rollback preview | Missing | No complete state-changing workflow. | Unverified | Documented: review and revert, code scope [C3] | Documented: checkpoint review [D1] | Require network-specific change scope and recovery plan before enabling writes. | P1 | 3 Trusted work | Network change backend and approval receipt | Review displays affected devices and rollback limits; chat revert never substitutes for device rollback. | Not started | Proposed | architecture.json; intentgraph/agent-runtime.cjs:203-214,271-415
UX-081 | Network | Comparison of diagnostic runs | Missing | No dedicated before/after evidence comparison. | Unverified | Documented: review scope comparison [C3] | Documented: diff review [D1] | Compare selected runs with time, target and evidence alignment. | P2 | 3 Trusted work | Durable evidence store | Different devices/times are labeled; missing results are not represented as zero change. | Not started | Proposed | polished.js evidence UI; intentgraph/agent-runtime.cjs:203-214,271-415
UX-082 | Network | Topology and visual evidence | Not verified | Topology specialist exists; interactive topology output not established. | Unverified | Documented: visualizations [C1] | Unverified | Add traceable network diagrams only when backed by actual inventory. | P2 | 4 Extend | Topology data contract | Nodes/links identify source and freshness; inferred links are labeled. | Not started | Investigate | Runtime/output verification needed; intentgraph/agent-runtime.cjs:203-214,271-415
UX-083 | Automation | Feed / activity inbox | Present | Feed derives entries from actual saved run messages and opens their exact message. Empty views explain what will appear. | Observed: unread dots and message activity [G1] | Observed: activity/notification icon [C0] | Unverified | Use an attention inbox for failed, finished and waiting investigations. | P2 | 3 Trusted work | Run events and notification routing | Every entry opens relevant run; empty view explains what will appear. | Verified | Proposed | 2026-09-16: workspace-shell.json; verify-workspace-tools.cjs 30 checks. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-084 | Automation | Ideas view | Present | Ideas can be created, edited, archived and restored with local persistence and save-failure recovery. No seed records. | Unverified | Unverified | Unverified | Remove from primary navigation until a useful workflow is defined. | P2 | 2 Chat | Product information architecture | No dead-end primary navigation; saved user ideas remain recoverable. | Verified | Proposed | 2026-09-16: workspace-shell.json; verify-workspace-tools.cjs 30 checks. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-085 | Automation | Goals and task checklist | Present | Local goals and checklist steps require real message evidence for completion. Manual completion is labeled, references remain inspectable, and missing references are explicit. | Unverified | Documented: goals and long-running work [C5] | Documented: task list [D2] | Show outcome, steps, evidence and blockers before promising autonomous goals. | P2 | 3 Trusted work | Durable task state | Completed step links to evidence; manual checklist state is not agent execution proof. | Verified | Proposed | 2026-09-16: verify-workspace-tools.cjs 30 checks; workspace-shell.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-086 | Automation | Scheduled investigations | Missing | No user-facing durable scheduling workflow. | Observed: routine panel and paused routine [G1] | Documented: schedules and in-chat follow-ups [C7] | Documented: recurring tasks [D3] | Add preview, timezone, pause/resume, last/next run and run history. | P2 | 4 Extend | Scheduler and authorization limits | Disabled schedule does not run; next-run time is correct; failures are visible. | Not started | Proposed | polished.html; server.cjs; polished.js:434-449; intentgraph/ui/index.html:7-8
UX-087 | Automation | Completion and attention alerts | Partial | Deduplicated local completion notices link to the correct result and respect mute. Broader attention/system alerts remain pending. | Observed: unread state and notification setting [G1] | Documented: notifications [C1] | Unverified | Notify only for meaningful completion, failure or required input. | P1 | 3 Trusted work | Notification channel | Alert opens correct task and respects mute; duplicate events do not spam. | Implemented | Proposed | 2026-09-16: alerts.json. Implemented slice verified; full feature remains pending.
UX-088 | Automation | Plugin discovery and management | Placeholder | Network connections surface is not a general plugin lifecycle. | Observed: Plugins entry [G1] | Observed: Plugins navigation [C0] | Documented: plugins/connectors [D1] | Prioritize real network adapters; expose install/connect/capability state accurately. | P2 | 4 Extend | Plugin/adaptor registry | Unavailable tool cannot be selected; permissions and connection health are visible. | Not started | Proposed | polished.html plugins pane; polished.js:434-449; intentgraph/ui/index.html:7-8
UX-089 | Automation | Skills and reusable workflows | Partial | Coworker documents exist; no complete skills browser/workflow picker. | Unverified | Documented: skills and plugins [C6] | Documented: skills/plugins [D1] | Add saved diagnostic procedures with purpose, inputs and evidence requirements. | P2 | 4 Extend | Workflow schema/runtime | Selected procedure identifies required access; version used is traceable. | Not started | Proposed | polished.js documents; runtime; polished.js:434-449; intentgraph/ui/index.html:7-8
UX-090 | Automation | Mobile or remote handoff | Missing | Local browser prototype and localhost runtime. | Unverified | Documented: remote work [C5] | Documented: Dispatch/remote sessions [D1] | Defer until identity, remote runtime and resumability are implemented. | P3 | 4 Extend | 2026-09-16 user decision: keep cross-device history, accounts/customer isolation and remote handoff pending; finish local features first. | Handoff preserves context and permissions without concurrent duplicate execution. | Deferred | Proposed | architecture.json; polished.js:434-449; intentgraph/ui/index.html:7-8
UX-091 | Quality | Keyboard-only operation | Partial | Named buttons and some keyboard handlers exist; full audit not run. | Unverified | Documented: documented shortcuts [C4] | Documented: keyboard shortcuts [D2] | Verify every primary chat/profile/menu workflow without a mouse. | P1 | 2 Chat | Interaction audit | Visible focus, logical order, no traps; Escape returns focus correctly. | Not started | Proposed | polished.html; polished.js keyboard handlers; polished.css:45-64,116-143,325-329; polished.js:19-58,437-449
UX-092 | Quality | Accessible names and state | Partial | Controls have many labels; Agent terminology and tab state need review. | Observed: reaction toggle labels observed [G1] | Unverified | Unverified | Use accurate roles, names and selected/busy states. | P1 | 2 Chat | Accessibility audit | Screen reader identifies each action, selected coworker and active run state correctly. | Not started | Proposed | A0 AX tree; polished.html; polished.css:45-64,116-143,325-329; polished.js:19-58,437-449
UX-093 | Quality | Contrast, text scaling and reflow | Present | Measured dark/light text contrast and tested 200% computed font scaling with usable controls. Narrow content reflows in tested Chromium views. | Unverified | Unverified | Unverified | Check selected WCAG 2.2 AA criteria and common desktop zoom levels. | P1 | 2 Chat | Theme/viewport audit | At 200% text scale controls remain usable; contrast measured; narrow content reflows. | Verified | Investigate | 2026-09-16: accessibility-results.json; scoped checks, not a full WCAG conformance claim. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-094 | Quality | Reduced motion | Present | Reduced-motion mode cancels decorative animation while state changes remain visible. Forced-colors scrollbar fallback verified. | Unverified | Unverified | Unverified | Respect reduced motion without hiding progress or breaking focus. | P2 | 2 Chat | Motion preference checks | Motion-reduced mode preserves all state changes and cancels decorative animation. | Verified | Proposed | 2026-09-16: accessibility-results.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-095 | Quality | Hover, focus and touch menus | Present | Pointer, touch and keyboard menus remain within viewport. Arrow navigation and Escape focus return pass at tested widths. | Observed: compact contextual actions [G1] | Unverified | Unverified | Keep actions discoverable by keyboard and touch without persistent clutter. | P1 | 2 Chat | UX-005 | Menus stay within viewport, remain operable on hover, close predictably and restore focus. | Verified | Proposed | 2026-09-16: accessibility-results.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-096 | Quality | Responsive pane layout | Present | Collapsed sidebar overflow corrected. Chat, panes and menus retain controls at 320/390/760/1440px and with 200% text stress. | Observed: profile pane reduces chat width [G1] | Observed: resizable split workspace [C0] | Documented: pane arrangement [D1] | Keep composer and selected context usable with sidebar and evidence pane open. | P1 | 2 Chat | Overflow containment and pane layout | Desktop, narrow window and zoomed layouts retain controls; deliberate table scroll is contained. | Verified | Proposed | 2026-09-16: accessibility-results.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-097 | Quality | Empty and unavailable states | Partial | Feed empty, artifacts sample-only, Settings not-connected states exist. | Unverified | Unverified | Unverified | Explain what to do next and remove dead-end primary entries. | P1 | 2 Chat | Capability inventory | Every visible action has a real result or an accurate reason it is unavailable. | Not started | Proposed | A0 Feed, Artifacts, Settings; polished.css:45-64,116-143,325-329; polished.js:19-58,437-449
UX-098 | Quality | Recoverable errors | Partial | Request errors surfaced; broad failure UX needs end-to-end checks. | Unverified | Unverified | Unverified | Preserve draft/evidence and offer relevant retry, reconnect or inspect action. | P1 | 3 Trusted work | Structured errors | Offline, timeout, cancellation and provider failure are distinct and recoverable. | Not started | Proposed | polished.js request handlers; server.cjs; polished.css:45-64,116-143,325-329; polished.js:19-58,437-449
UX-099 | Quality | Long transcript performance | Not verified | No large-history performance result established. | Unverified | Unverified | Unverified | Measure before adding virtualization; preserve search and evidence anchors. | P2 | 3 Trusted work | Large transcript fixture | Long chat stays responsive and scrolling does not lose selection or anchors. | Not started | Investigate | Performance check not run; polished.css:45-64,116-143,325-329; polished.js:19-58,437-449
UX-100 | Quality | First-run onboarding | Partial | Coworker creation and welcome exist; setup remains fragmented. | Observed: bot-first chat entry [G1] | Observed: new chat/project entry [C0] | Documented: environment, folder, model, mode setup [D1] | Guide user from provider/connection readiness to first useful read-only investigation. | P1 | 3 Trusted work | Provider and connection state | A new user understands required setup, selected device and next safe action. | Not started | Proposed | A0; polished.js initialization; polished.css:45-64,116-143,325-329; polished.js:19-58,437-449
UX-101 | Quality | Saved state and migration integrity | Partial | Versioned migration and backup exist; production storage reliability remains limited. | Unverified | Unverified | Unverified | Keep explicit schema versions and recoverable migrations. | P1 | Keep | Migration regression | Chats, drafts, queued work, avatars and revert history survive migration exactly. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/runtime/verify-backup-schema.cjs:4-28 (current six backup/transaction/size tests); .intentgraph/evidence/ux-fixes-2026-09-15/local-data-ui.json (roundtrip/Add/replace/reload); .intentgraph/evidence/ux-fixes-2026-09-15/history-regression.json (revert/avatar/history) Owner acceptance remains separate.
UX-102 | Quality | Release identity and diagnostics | Present | About identifies the loaded build and offers a user-triggered local configuration snapshot and safe support copy. Unverified reachability is explicit. | Unverified | Unverified | Unverified | Expose build version, connection status and safe diagnostics export. | P2 | 3 Trusted work | Connection diagnostics must read the current backend/provider state without exposing credentials. | Support report identifies exact build and contains no provider keys. | Verified | Proposed | 2026-09-16: diagnostics-ui.json; verify-chat-read-api.cjs. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-103 | Quality | Consistent terminology and icon system | Present | Coworker, Conversation and Evidence labels aligned across navigation, profile, Settings and composer; storage schema retained. | Observed: bot identity consistent in inspected flow [G1] | Observed: task/project labels [C0] | Documented: session/environment labels [D1] | Use Coworker, Conversation and Evidence consistently for network users. | P1 | 2 Chat | UX-007 | Same object keeps same name across sidebar, profile, Settings and composer. | Verified | Agreed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/{root-review.json,history-regression.json,reaction-recovery.json}; isolated browser checks exit 0. No provider/device calls; no physical-device or owner acceptance.
UX-104 | Quality | Multiple customer isolation UX | Missing | No authenticated customer workspaces or access control service. | Unverified | Unverified | Unverified | Treat as later product architecture; never imply current shared-team security. | P1 | 4 Extend | 2026-09-16 user decision: keep cross-device history, accounts/customer isolation and remote handoff pending; finish local features first. | Wrong-customer data is inaccessible; workspace/access context is explicit. | Deferred | Proposed | architecture.json; polished.css:45-64,116-143,325-329; polished.js:19-58,437-449
UX-105 | Quality | Professional finish acceptance | Not verified | Automated checks previously passed; owner rejected specific UI decisions. | Unverified | Unverified | Unverified | Verify agreed reference behaviors and complete flows before marking accepted. | P1 | 2 Chat | All phase 1 corrections | Code check, rendered behavior and owner acceptance have separate recorded outcomes. | Not started | Investigate | User feedback; current audit; polished.css:45-64,116-143,325-329; polished.js:19-58,437-449
UX-106 | Network | Live inventory and read-only diagnostics | Present | Real inventory and allowlisted exact-host diagnostic path exist. | Unverified | Unverified | Unverified | Keep exact target resolution and bounded output visible. | P1 | Keep | Adapter regression | Only supported read-only commands execute; failed transport cannot be shown as healthy. | Verified | Preserve | 2026-09-16: preservation audit PASS. 25/25 local fixture tests passed: agent-runtime/chat-runtime/network-execution/sandbox-routes/steering suites (allowlist, exact target, failed transport, read-only origin/header); no provider/device calls Owner acceptance remains separate.
UX-107 | Network | Remote command cancellation limits | Present | Cancellation stops local fetch and propagates to the server; already submitted remote work is explicitly UNKNOWN, with retained evidence and no automatic duplicate retry. | Unverified | Unverified | Unverified | Explain that stopping the UI may leave remote work outcome unknown. | P1 | 3 Trusted work | Transport cancellation support | Stop records UNKNOWN when remote completion cannot be established; no automatic duplicate retry. | Verified | Proposed | 2026-09-16: verify-queue-terminal.cjs 4/4; run-durability.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-108 | History | Context truncation disclosure | Present | Context preview uses the request helper: latest 24 stored messages, 32,000 characters, and visible omission count. Local welcomes and notes excluded. | Unverified | Unverified | Documented: context usage [D1] | Show retained context and offer a reviewed summary for long investigations. | P1 | 3 Trusted work | Runtime context contract | User can tell when older messages are omitted; raw historical evidence stays available. | Verified | Proposed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/chat-interactions.json; verify-chat-interactions.cjs exit 0. Mocked requests; owner acceptance pending.
UX-109 | Coworkers | Local notes versus model memory | Present | Profile and document editor disclose local-only notes. Saving works; mocked request evidence confirms notes are not sent to the model. | Unverified | Documented: agent instructions [C6] | Documented: shared configuration [D1] | Label local-only notes now; connect them only with clear review and scope. | P1 | 2 Chat | Document/runtime context contract | Editing local note never implies the next model response used it unless request evidence proves inclusion. | Verified | Agreed | 2026-09-15: .intentgraph/evidence/ux-fixes-2026-09-15/{root-review.json,history-regression.json,reaction-recovery.json}; isolated browser checks exit 0. No provider/device calls; no physical-device or owner acceptance.
UX-110 | Messages | Safe links and inline media | Partial | HTTP(S) links use safe new-window/referrer attributes. Unsafe schemes and HTML are inert. Image references are explicit links; inline media and attachment reading remain pending. | Unverified | Documented: image/file outputs [C1] | Documented: file previews [D1] | Add safe links and supported media without executing untrusted content. | P2 | 2 Chat | Inline media needs explicit loading policy; attachment contents need a validated backend contract. | Links open correct source; unsupported media remains a labeled file; raw CLI remains unchanged. | Implemented | Proposed | 2026-09-15: edit-rendering.json and verify-edit-rendering.cjs exit 0 validate safe-link slice only. Full media acceptance remains pending.
UX-111 | Navigation | Mark read or unread | Present | Local unread and conversation actions exist. | Observed: unread dot and NEW separator [G1] | Documented: mark chat unread [C4] | Unverified | Keep manual unread state separate from active execution state. | P2 | Keep | Unread persistence check | Unread state persists correctly; opening a conversation never cancels work. | Verified | Preserve | 2026-09-16: preservation audit PASS. .intentgraph/evidence/pending-88-20260916/preserved-audit.json (beforeOpen=true, afterOpen=false; no request path) Owner acceptance remains separate.
UX-112 | Settings | Language support disclosure | Present | The language selector explicitly identifies English as the system fallback; unsupported translations cannot appear selected or applied. | Unverified | Unverified | Unverified | Keep unsupported locales disabled; translate complete workflows only when supported. | P3 | 4 Extend | Localization and text expansion | Language choice never appears applied while labels remain unchanged. | Verified | Proposed | 2026-09-16: diagnostics-ui.json. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-113 | Execution | Serial capacity feedback | Present | Serial capacity feedback identifies the active coworker and offers navigation to the active conversation while preserving independent drafts and FIFO queue behavior. | Unverified | Observed: parallel task indicators [C0] | Documented: parallel sessions [D1] | Explain when another conversation occupies runtime and where queued work will run. | P1 | 3 Trusted work | Global busy state and queue ownership | Second conversation shows why it waits and identifies active work without losing its draft. | Verified | Proposed | 2026-09-16: alerts.json; verify-queue-terminal.cjs 4/4. Isolated tests passed; no live provider/device call. Owner acceptance pending.
UX-114 | Outputs | Existing approval tooling integration | Partial | IntentGraph has preview/approve/execute surfaces separate from Aven. | Unverified | Documented: review panel [C3] | Documented: diff/permission controls [D1] | Reuse proven backing contracts; design Aven-facing review without exposing engineering internals. | P1 | 3 Trusted work | IntentGraph execution-service integration | Aven preview and executed action share the same digest, scope and one-time approval. | Not started | Proposed | intentgraph/ui/index.html:7-8; adapters/index.cjs:462-503,570-598
UX-115 | History | Durable raw run records | Present | Backend writes run evidence files even though model checkpoints are in memory. | Unverified | Unverified | Unverified | Preserve run records and expose retrieval from the relevant conversation. | P1 | Keep | Evidence retention and access | A saved run record is retrievable with original provenance after UI reload. | Verified | Preserve | 2026-09-16: preservation audit PASS. isolated `verify-chat-read-api.cjs` passed (original raw provenance/read-back; secret fields stripped); .intentgraph/evidence/pending-88-20260916/run-recovery.json (reload/deep links/durable capture) Owner acceptance remains separate.
[5 empty] | Source key | Source / scope | Location | Coverage / limitation
[5 empty] | A0 | Live Aven, 15 Sep 2026 | http://127.0.0.1:8767/polished.html?revision=direct-teams-v4 | Chat, message actions, profile, account, Settings, archive empty state, Feed and artifacts inspected. No provider requests sent.
[5 empty] | G1 | Grok Bot 0.27.0 | Installed Windows app; .intentgraph/evidence/ux-comparison-2026-09-15/ | Firewall chat/menu/profile and creation menu inspected. TAPE routine/choice card observed. Reactions were not changed. No execution or notification delivery test.
[5 empty] | C0 | Codex app 26.908.4834.0 | Installed Windows app; codex-workspace.png | Current task, progress, model/effort, stop, sidebar and actual embedded Aven browser observed. Not a complete live feature test.
[5 empty] | C1 | OpenAI feature overview | https://learn.chatgpt.com/docs/features | Official former Codex app docs redirect to ChatGPT Learn. Scope is desktop/Codex where identified; availability may vary.
[5 empty] | C2 | OpenAI projects and chats | https://learn.chatgpt.com/docs/projects | Use desktop sections, not web/CLI behavior.
[5 empty] | C3 | OpenAI code review | https://learn.chatgpt.com/docs/code-review | Diff scopes, inline feedback, stage/revert and repository workflows.
[5 empty] | C4 | OpenAI commands | https://learn.chatgpt.com/docs/reference/commands | Windows desktop shortcuts and documented affordances.
[5 empty] | C5 | OpenAI long-running work | https://learn.chatgpt.com/docs/features | Long-running and remote entries are documented links; full recovery semantics not independently verified.
[5 empty] | C6 | OpenAI developer feature index | https://learn.chatgpt.com/docs/features | Documents/instructions, terminals, approvals, skills and environment links. Indexed features are not live-tested here.
[5 empty] | C7 | OpenAI scheduled tasks | https://learn.chatgpt.com/docs/automations | Desktop recurring tasks and in-chat follow-ups.
[5 empty] | D0 | Claude Windows 1.52386.0.0 | claude-code-access.png | Code tab shows Get Claude Code. Working Code session is access-gated; chat home is not Code capability proof.
[5 empty] | D1 | Claude Code desktop | https://code.claude.com/docs/en/desktop | Official documentation, not live working-session verification.
[5 empty] | D2 | Claude Code terminal interaction | https://code.claude.com/docs/en/interactive-mode | CLI-only affordances are labeled. Do not assume desktop uses identical commands or shortcuts.
[5 empty] | D3 | Claude Code schedules | https://code.claude.com/docs/en/desktop | Desktop docs list recurring tasks; detailed local scheduling operation not tested.
[5 empty] | A1 | Current active Aven source | polished.html, polished.css, polished.js; intentgraph/server.cjs; intentgraph/agent-runtime.cjs | Code-supported presence is not proof of end-to-end behavior. Older index.html is excluded.
[5 empty] | Scope | Coverage limits | UI/UX and user-visible behavior | No exhaustive parity or accessibility certification. No production-device execution, paid model call, remote integration, or reference-message mutation was performed.
[5 empty] | Workflow | Use this register | Filter Phase, Aven state, Priority or Decision | Update Delivery and evidence per feature. Verified is tested behavior; Accepted requires owner feedback. Future editors must import this workbook and preserve user changes.
[5 empty] | Preservation | Required throughout | Chats, drafts, queues, avatars, raw CLI and revert history | Teams labels are not execution capability. Removing Teams navigation must retain reachable existing grouped histories. Device commands are never undone by chat revert.